## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 task | Any other metrics defined in your SPPP
0 | 5/9/2023 - 5/16/2023 | Project proposal and team member roles finalized Team weaknesses identified (Django Framework experience) |  | Abhishek has left the group, we made documentation on his project idea and thought of using React for Front End but he left the group at last minute. So we have to start with a new idea and redid the documentation. This added pressure on team members at the last minute. | Scheduled a weekly meeting ( wednesday and friday) to improve communication. | N/A | N/A | N/A | N/A | N/A | 40 | 37 | 3 | 14.5 | 3.5 | 0.5 | 0 |  | 4.5 | 5.5 | 8 | N/A
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Adithya_Prakash
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7.5 | 6.5 | 1 | 0 - Learn git & django fundamentals 2 - Look into the full tech stack design and implementation plan 5 - Take feedback from team on finalizing tech stack 6 - Git setup 7 - Compare and research on various tech stack options(most suitable for the Django framework) | 2 | 0.5 | 0.5 |  |  | 0.5 | 1 | 2 | 1. Writing SPPP 2. Git setup 3. 0th Iteration presentation | 1. Finalizing the tech stack for the project 2. Deciding the database between PostgreSQL v/s MySQL. | 1. Finding and analyzing pros and cons of different tech stack options 2. Looking into what database would be more ideal for our project. | 0 - Continue to learn about the best tech stack options 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Alekhya_Koppineni
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 8.5 | 6 | 2.5 | 0 - learn git and django, the project details and documents, learn miro, lucidchart, jira 1 - define high level requirements 5 - make project plan, send reminders to team members, set up zoom meetings 6 - set up git for lab 1 7 - iteration 0 work | 2 | 1 |  |  |  | 0.5 | 0.5 | 2 | 1. Wrote the sections of SPPP 2. Set up git, commited the introduction information 3. Started the Iteration 0 presentation | 1. need more familiarity with Django framework 2. had trouble with team member dropping out after almost all the work was done | 1. pratice with Django 2. try to check on members and thier tasks so that we dont wait till the last min | 0 - continue to learning goals 1 - continue to define requirements 3 - implement a basic hello world on Django 5- add more meetings and increase productivity in meetings 7- create lucid chart, iteration 1, progress report update | 6
2 | 05/17-23

## Corydon_Wood
Your Lead Roles: Backup Project Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7.5 | 5 | 2.5 | 0 - learn git and django, Jira, Researched industry best practices for git branching, Agile process, Django application architectures 1 - define high level requirements 6 - set up git, Miro, Jira 7 - research similar products, prepare presentation, | 2 | 0.5 |  |  |  |  | 2 | 0.5 | 1. Wrote 1 section of the SPPP 2. Drafterd the SPPP Risk Management document 3. Set up git, Miro, Jira project 4. Participate project design discussions | 1. Team member dropped the class late so the project topic changed which required rework 2. Need to stick to have more clear task assignments and accountability, team is rushing to get things done at the last minute | 1. Update SPPP and complete research for new product requirements by end of day 5/17 2. Start team planning sessions at the begining of iterations, begin using Jira to assign tasks | 0 - continue to learn Django 1 - Add high level requirements to Jira 3 - Implement code quality github Actions 6- Set up miro boards for planning, add github docs site, improve Jira boards | 9

## Jasmine Hughes
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 05/10-05/16 | 7.5 | 5 | 2.5 | 0 - learn git, read tutorials and watched videos 0 - learn basics of QA scope and testing 7 - worked on QA aspects of the SPPP doc | 3.5 | [6 empty] | 1.5 | 1. Write the Metrics and Testing sections of the SPPP 2. Set up git, commit the lad 1 portion | 1. Not familiar with QA and how to test/what's expected for it 2. Not familiar with Git and how it works | 1. Keep researching testing types and how to use Pytest for testing 2. Find YouTube channel dedicated to QA for software Engineering | 1. Research Django, ReactJS, GitHub, Pytest 2. Research additional testing applications for the database and app server 3. Research more about testing and QA | 6

## Edara_Umamaheswar
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 12.5 | 9.5 | 3 | 0 - learn git and django, Jira, Lucid Chart Diagram, Agile process, Django application architectures 1 - define high level requirements 5 - Assigned Individual tasks to everyone and Communicated about the Project Requirments. Followedup with all team members on their individual tasks and also reviewed all the documentation. 6 - set up git, Jira 7 - prepare presentation slides, presentation vedio, Reviewing all the Project Documentation . | 3 | 1 |  |  |  | 3 | 1 | 1.5 | 1. Write 3 sections of SPPP 2. Set up git, and adding all the required documents 3. Participate in Iteration 0 presentation | 1. Not familiar with Django and Jira Tool so learning them | 0 - In the process of learnign Django | 0 - will complete learning Django in one week | 10

## Zuowen_Tang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 6 | 5 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 2 | 0.5 | 0.5 |  |  | 0.5 | 1 | 0.5 | 1. Create Documents in Team Folder 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. A classmate has dropped out of the class. 2. I Was finishing the final week of BU spring semester. 3. Communication is not clear. We were talking back and forward about the same topic | 1. The spring semester will be ended next week. 2. Try to set up an actual plan and communicate clearly with people | 0 - Set up a clear plan for the summer term | 6
2 | 5/17-5/23

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6