## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personel | Loss team members | One or more team members drop the class | 5 | 4 | 4 | 8 | team leader and all members | 2023-05-16 | Redefine the project scope if necessary, and assign the tasks to other team members. | Regrouped as a team to discuss the pros and cons of swithching plans | Open
| add new team members | One or more people join the team | 3 | 2 | 2 | 24 | team leader and all members | 2023-05-16 |  |  | Open
| Lack of motivation or responsibility | One or more team members do not feel ownership of the product and do not contribute | 3 | 4 | 3 | 18 | team leader and all members |  | Allow all members to provide input in planning sessions and take ownership of certain features or requirements. Hold eachother accountable in review sessions. |  | Open
Communication | duplicate work | Multiple team members working on the same task with no coordination | 2 | 3 | 3 | 36 | All members | 2023-05-30 | Use Jira stories to assign tasks |  | Open
| worked on wrong components | Miscommunication results in incorrect components being developed | 1 | 4 | 2 | 20 | Configuration leader/Implementation Leader/ Team Leader |  | Write detailed story descriptions |  | Open
| useless work | Work does not add vlaue to the end product | 4 | 4 | 3 | 12 | Implementation Leader/ Team Leader |  | Consider value added for a story and detail the value in the story description |  | Open
Requirements | unclear requirements | Person assigned a task is unsure of what the desired outcome is | 4 | 5 | 3 | 6 | Requirement leader |  | Provide cleard definistions of done, and acceptence criteria for each story |  | Open
| scope creep | Additional tasks are added to a story, or feature after it has been created | 4 | 5 | 3 | 6 | Requirement leader | ongoing | Do not add stories to an iteration, clearly define function of deliverable component |  | Open
| constant requirements changes | Indecision on what the requirements for the product are result in development stalling, or work becoming useless | 3 | 4 | 3 | 18 | Requirement leader | ongoing | Define objective functional requirements and drive |  | Open
Management | improper task assignments | Someone is assigned a taks they are not familiar with or do not have the skills to accomplish | 1 | 3 | 2 | 30 | Team leader/Configuration leader | ongoing | Hold iteration planning sessions as a team so that we collectively review and assign tasks |  | Open
| improper planning | Lack of planning results in disjointed components beign developed | 2 | 3 | 2 | 24 | Configuration leader/Implementation Leader/ Team Leader | ongoing | Hold team iteration planning sessions at the begining of the iteration |  | Open
| lack of management skills | Leadership gaps result in team members not being engaged, unclear direction | 2 | 4 | 3 | 24 | team leader and all members | ongoing | Team members and the team leader must be able to hold one another accountable, manage time, and provide constructive feedback |  | Open
Technology competence | Not familiar with the framework used | Team memebrs have nto previously used Django | 4 | 4 | 4 | 16 | team leader and all members | 2023-05-30 | Share helpful links and tutorials in team channel |  | Open
| Not familiar with the programming language used | Team members have not previously used python | 2 | 4 | 3 | 24 | team leader and all members | 2023-05-30 | Share helpful links and tutorials in team channel |  | Open
| Not familiar with unit testing | Lack of unit testing or poorly written tests lead to defects makign their way into production | 3 | 3 | 2 | 18 | QA leader | 2023-05-30 | Encourage self learning, create example tests, and check testing coverage during iteration reviews |  | Open
| Other technology incompetence | Lack of experience with technology increases the delivery time for components | 5 | 3 | 3 | 9 | Configuration leader | 2023-05-30 | Assign tasks to team members most comfortable with the given technology |  | Open
| Not familiar with Git | Team member is not familiar with Git commands or version control | 4 | 2 | 2 | 16 | Configuration leader | 2023-05-16 | Use git documentation to learn commands and best practices | Reviewed GitHub in iteration 0 team meeting | Open
Design and implementation | Improper design | Design of application does not allow for the features to be implemented | 3 | 4 | 3 | 18 | Design and Implementation Leader | 2023-05-30 | Review industry best practices for the framework and develop architecture before programming |  | Open
| improper technology stack | Layers of the technology stack are not synerystic and creat inefficiences or defects | 2 | 5 | 2 | 8 | Design and Implementation Leader | 2023-05-30 | Review industry best practices |  | Open
| Messy code | Lack of adherence to code quality standards leads to defects and time lost to maintaining existing code | 4 | 3 | 2 | 12 | Design and Implementation Leader | 2023-05-30 | Perform code reviews before merging and establish code conventions and quality standards early on |  | Open
Testing | Not enough testing | Lack of tests results in bugs or difficult integration | 3 | 4 | 4 | 24 | QA leader | 2023-06-13 | Invest the time up front to write tests as new pieces of code are added so that they can be automatically tested in the future |  | Open
Integration and deployment | Not enough time for integration and deployment | New code is not integrated properly which leads to defects | 3 | 5 | 4 | 12 | Configuration leader | 2023-05-30 | Create automated CI/CD pipelines to reduce repatitive manual tasks |  | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.