## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personel | Loss team members | One or more team members drop the class | 5 | 4 | 4 | 8 | team leader and all members | 2023-05-16 | Redefine the project scope if necessary, and assign the tasks to other team members. | Regrouped as a team to discuss the pros and cons of swithching plans. Lost multiple members reperformed planning sessions tried to resope the iteration, maybe did not reduce as much as we should have | Closed
| add new team members | One or more people join the team | 3 | 2 | 2 | 24 | team leader and all members | 2023-05-16 |  |  | Closed
| Lack of motivation or responsibility | One or more team members do not feel ownership of the product and do not contribute | 3 | 4 | 3 | 18 | team leader and all members | Ongoing | Allow all members to provide input in planning sessions and take ownership of certain features or requirements. Hold eachother accountable in review sessions. |  | Open
Communication | duplicate work | Multiple team members working on the same task with no coordination | 2 | 3 | 3 | 36 | All members | 2023-06-28 | Use Jira stories to assign tasks | Jira stories and tasks were have been created to distribute tasks between team members. This has worked well so far. | Open
| worked on wrong components | Miscommunication results in incorrect components being developed | 3 | 4 | 2 | 12 | Configuration leader/Implementation Leader/ Team Leader |  | Write detailed story descriptions. Create clear acceptence criteria. | Added descriptions to all user stories. In Iteration 2 we should add AC to tasks as well. | Open
| useless work | Work does not add vlaue to the end product | 4 | 4 | 3 | 12 | Implementation Leader/ Team Leader | ongoing | Consider value added for a story and detail the value in the story description |  | Open
Requirements | unclear requirements | Person assigned a task is unsure of what the desired outcome is | 4 | 5 | 3 | 6 | Requirement leader | ongoing | Provide cleard definistions of done, and acceptence criteria for each story |  | Open
| scope creep | Additional tasks are added to a story, or feature after it has been created | 3 | 5 | 3 | 9 | Requirement leader | ongoing | Do not add stories to an iteration, clearly define function of deliverable component |  | Open
| constant requirements changes | Indecision on what the requirements for the product are result in development stalling, or work becoming useless | 3 | 4 | 3 | 18 | Requirement leader | ongoing | Define objective functional requirements and drive |  | Open
Management | improper task assignments | Someone is assigned a taks they are not familiar with or do not have the skills to accomplish | 1 | 3 | 2 | 30 | Team leader/Configuration leader | ongoing | Hold iteration planning sessions as a team so that we collectively review and assign tasks |  | Open
| improper planning | Lack of planning results in disjointed components beign developed | 2 | 3 | 2 | 24 | Configuration leader/Implementation Leader/ Team Leader | ongoing | Hold team iteration planning sessions at the begining of the iteration |  | Open
| lack of management skills | Leadership gaps result in team members not being engaged, unclear direction | 2 | 4 | 3 | 24 | team leader and all members | ongoing | Team members and the team leader must be able to hold one another accountable, manage time, and provide constructive feedback |  | Open
Technology competence | Not familiar with the framework used | Team memebrs have not previously used Django | 5 | 4 | 4 | 8 | team leader and all members | 2023-06-26 | Share helpful links and tutorials in team channel | Will Set aside more time for learning and take that into account when estimating the cost for tasks | Open
| Not familiar with the programming language used | Team members have not previously used python | 2 | 4 | 3 | 24 | team leader and all members | 2023-05-30 | Share helpful links and tutorials in team channel |  | Open
| Not familiar with unit testing | Lack of unit testing or poorly written tests lead to defects makign their way into production | 3 | 3 | 2 | 18 | QA leader | 2023-06-06 | Encourage self learning, create example tests, and check testing coverage during iteration reviews |  | Open
| Other technology incompetence | Lack of experience with technology increases the delivery time for components | 5 | 3 | 3 | 9 | Configuration leader | 2023-05-30 | Assign tasks to team members most comfortable with the given technology |  | Open
| Not familiar with Git | Team member is not familiar with Git commands or version control | 4 | 2 | 2 | 16 | Configuration leader | 2023-05-16 | Use git documentation to learn commands and best practices | Reviewed GitHub in iteration 0 team meeting | Closed
Design and implementation | Improper design | Design of application does not allow for the features to be implemented | 3 | 4 | 3 | 18 | Design and Implementation Leader | 2023-05-30 | Review industry best practices for the framework and develop architecture before programming |  | Open
| improper technology stack | Layers of the technology stack are not synerystic and creat inefficiences or defects | 2 | 5 | 2 | 8 | Design and Implementation Leader | 2023-05-30 | Review industry best practices |  | Open
| Messy code | Lack of adherence to code quality standards leads to defects and time lost to maintaining existing code | 4 | 3 | 2 | 12 | Design and Implementation Leader | 2023-05-30 | Perform code reviews before merging and establish code conventions and quality standards early on |  | Open
Testing | Not enough testing | Lack of tests results in bugs or difficult integration | 3 | 4 | 4 | 24 | QA leader | 2023-06-13 | Invest the time up front to write tests as new pieces of code are added so that they can be automatically tested in the future |  | Open
Integration and deployment | Not enough time for integration and deployment | New code is not integrated properly which leads to defects | 3 | 5 | 4 | 12 | Configuration leader | 2023-05-30 | Create automated CI/CD pipelines to reduce repatitive manual tasks |  | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.