## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 task | Any other metrics defined in your SPPP
0 | 5/9/2023 - 5/16/2023 | Project proposal and team member roles finalized Team weaknesses identified (Django Framework experience) |  | Abhishek has left the group, we made documentation on his project idea and thought of using React for Front End but he left the group at last minute. So we have to start with a new idea and redid the documentation. This added pressure on team members at the last minute. | Scheduled a weekly meeting ( wednesday and friday) to improve communication. | N/A | N/A | N/A | N/A | N/A | 40 | 37 | 3 | 14.5 | 3.5 | 0.5 | 0 |  | 4.5 | 5.5 | 8 | N/A
1 | 5/16/2023 - 5/30/2023 | completed important user stories and project demo is made.user login, registration, db and db design is done and we are working on implementing other features |  | Issue with Meeting Timings and individual updates | We are using online tool to identify the common timings for evryone | [5 empty] | 88 | 82 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Adithya_Prakash
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7.5 | 6.5 | 1 | 0 - Learn git & django fundamentals 2 - Look into the full tech stack design and implementation plan 5 - Take feedback from team on finalizing tech stack 6 - Git setup 7 - Compare and research on various tech stack options(most suitable for the Django framework) | 2 | 0.5 | 0.5 |  |  | 0.5 | 1 | 2 | 1. Writing SPPP 2. Git setup 3. 0th Iteration presentation | 1. Finalizing the tech stack for the project 2. Deciding the database between PostgreSQL v/s MySQL. | 1. Finding and analyzing pros and cons of different tech stack options 2. Looking into what database would be more ideal for our project. | 0 - Continue to learn about the best tech stack options 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
2 | 05/17-05/23 | 11 | 10 | 0.5 | 0 - Learn django fundamentals for postgre and react integrations 2 - Look into the full stack implementation details - how to integrate 5 - Take feedback from team on implementing stack 6 - Git setup for each iteration - Git rebase(ideal) 7 - Look into how much features to be implemented based on research | 2 | 1 | 2.5 |  |  | 1.5 | 0.5 | 2.5 | Decide backend implementation plan | Exact user stories | Decidiing priority of user stories | Will need to look into highest priority items first. | 10
3 | 05/24-05/30 | 11.5 | 11 | 0.5 | 0 - Learn Postgre details for db implementation 2 - Look into how to integrate postgre with django 5 - Take feedback from team on implementing db 6 - Git repo check for each iteratn 7 - Look into which approach to use to implement based on research | 2 | 2.5 | 1 |  |  | 1.5 | 0.5 |  | Decide db complete implementation plan | How to integrate various features in the correct manner | Deciding the db ui and calorie functionality details | Continue to look into the design plan and see the feasibility of implementation | 11

## Alekhya_Koppineni
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 8.5 | 6 | 2.5 | 0 - learn git and django, the project details and documents, learn miro, lucidchart, jira 1 - define high level requirements 5 - make project plan, send reminders to team members, set up zoom meetings 6 - set up git for lab 1 7 - iteration 0 work | 2 | 1 |  |  |  | 0.5 | 0.5 | 2 | 1. Wrote the sections of SPPP 2. Set up git, commited the introduction information 3. Started the Iteration 0 presentation | 1. need more familiarity with Django framework 2. had trouble with team members dropping out after almost all the work was done | 1. pratice with Django 2. try to check on members and thier tasks so that we dont wait till the last min | 0 - continue to learning goals 1 - continue to define requirements 3 - implement a basic hello world on Django 5- add more meetings and increase productivity in meetings 7- create lucid chart, iteration 1, progress report update | 6
2 | 05/17-23 | 7 | 4 | 3 | 0 - learning jira 3 - implemented a basic hello world on Django 5 - communicated meeting time availabilities, set meeting plans 7 - iteration 1 work, lab 2, updating progress report, quiz 1 | 1 |  |  | 1 |  | 0.5 |  | 1.5 | 1. updated SPPP 2. created user stories in SPPP 3. added acceptance criteria in jira | 1. new to jira 2. schdueling issues | 1. getting more familiar with jira with practice 2. constantly wokring around schduels and recording meetings for reference. | 0- continue to learning goals 3 - gain more experince with jira 5- add more meetings and increase productivity in meetings, start stand ups 7- lab3, iteration 2, progress report update | 4
3 | 05/24-05/30 | 4 | 2 | 2 | 0 - github and jira usage 3 - updated sdd file | 2 |  |  | 1 |  |  |  | 1 | 1. updated SDD | 1. had a last minute emergency causing unavailablity 2. did not make much new progress due to missed time this week | 1. will make a better attamept at not waiting till the last min in case of future unavailabilities 2. review missed meetings and put in more effort in the next steps | 0 - continue learning git, jira, Django 1- Iteration 2 steps | 12

## Corydon_Wood
Your Lead Roles: Backup Project Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7.5 | 5 | 2.5 | 0 - learn git and django, Jira, Researched industry best practices for git branching, Agile process, Django application architectures 1 - define high level requirements 6 - set up git, Miro, Jira 7 - research similar products, prepare presentation, | 2 | 0.5 |  |  |  |  | 2 | 0.5 | 1. Wrote 1 section of the SPPP 2. Drafterd the SPPP Risk Management document 3. Set up git, Miro, Jira project 4. Participate project design discussions | 1. Team member dropped the class late so the project topic changed which required rework 2. Need to stick to have more clear task assignments and accountability, team is rushing to get things done at the last minute | 1. Update SPPP and complete research for new product requirements by end of day 5/17 2. Start team planning sessions at the begining of iterations, begin using Jira to assign tasks | 0 - continue to learn Django 1 - Add high level requirements to Jira 3 - Implement code quality github Actions 6- Set up miro boards for planning, add github docs site, improve Jira boards | 9
2 | 05/17-05/23 | 8 | 6 | 2 | "0 - django, Jira, Flake8 Researched industry best practices for git branching, Agile process, Django application architectures 1 - define high level requirements 6 - set iteration1 in Jira added user stories created tasks 5-Held team planning session, created git branches in the repository for branching strategy " | 3 | 1 |  |  |  | 1 | 1
3 | 05/24-05/30 | 18 | 16 | 2 | 0 - Researched Jekyll and Flake8 for github site and linting action respectively 3 - Developed login API endpoints, revised login page HTML, Consolidated team member code contributions, create GitHub site for documentation 4- Created tests in postman for APIs 5- Wrote how to guides on setting up development environment and how to add a documentation page to the site, updated jira tasks 6 - Dockerized application & database, managed github branches and PRs | 2 |  |  | 8 | 1 | 2 | 3 |  | Created Demo Created Iteration 1 presentation Updated Risks document Recorded demo and presentation videos | 1. Lots of last minute meeting equests made it hard to get all team members together 2. Limited updates from some team members resulted in suprises at the end of the iteration | 1 Schedule a set meeting cadence 2 Encourage heavier use of Jira stories and providing updates in them | 0 - Focus on learning Django 1- Analyze stories and tasks for iteration 2 3- Build out API calls for food database 4 - Write pytests for API functions 5 - Set up jira for iteration 2 | 12

## Jasmine Hughes
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 05/10-05/16 | 7.5 | 5 | 2.5 | 0 - learn git, read tutorials and watched videos 0 - learn basics of QA scope and testing 7 - worked on QA aspects of the SPPP doc | 3.5 | [6 empty] | 1.5 | 1. Write the Metrics and Testing sections of the SPPP 2. Set up git, commit the lad 1 portion | 1. Not familiar with QA and how to test/what's expected for it 2. Not familiar with Git and how it works | 1. Keep researching testing types and how to use Pytest for testing 2. Find YouTube channel dedicated to QA for software Engineering | 1. Research Django, ReactJS, GitHub, Pytest 2. Research additional testing applications for the database and app server 3. Research more about testing and QA | 6

## Edara_Umamaheswar
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 12.5 | 9.5 | 3 | 0 - learn git and django, Jira, Lucid Chart Diagram, Agile process, Django application architectures 1 - define high level requirements 5 - Assigned Individual tasks to everyone and Communicated about the Project Requirments. Followedup with all team members on their individual tasks and also reviewed all the documentation. 6 - set up git, Jira 7 - prepare presentation slides, presentation vedio, Reviewing all the Project Documentation . | 3 | 1 |  |  |  | 3 | 1 | 1.5 | 1. Write 3 sections of SPPP 2. Set up git, and adding all the required documents 3. Participate in Iteration 0 presentation | 1. Not familiar with Django and Jira Tool so learning them | 0 - In the process of learnign Django | 0 - will complete learning Django in one week | 10
2 | 05/16 - 05/23 | 12.5 | 10.5 | 2 | Individual Task Breakdown 0 - Django framework, Jira, Researched about the industry best practices for django application development 1 - discussed about the requiremts with the requirments leader 3 - Created the Django Base code, Implemented the Login page and Login CSS, finalized the project file structure 5 - Intioalized 2 team meetings and discussed project related tasks assignemnt and time line constraints 6 - Created virtual envoronment for the Project, so that all the files required for the project are installed in a seperate environment. | 2 | 1 |  | 6 |  | 0.5 | 1 |  | Implemented the Logion page, registration page an duser page along with CSS part. Implemented registration validation form and about to complete the calorie tracting. Updated the GITHUB Repository with the latesat code base |  |  | work on iteration1 taks | 10
3 | 05/23 - 05/30 | 16 | 15 | 1 | Individual Task Breakdown 0 - Application Architecture, Django views and other features 1 - We are discussing on modifying the user page requiermnts(implementing a form for calorie value, input from user instead of extracting that value from external API's ) 3 - implemented the Registration page and css,Valid registraction JS script, along with that updated the Project Readme.md file for better understanding on how to run this application 5 - Expressed Concern about the Meeting arrangments and delayed functionality implmentation, reached out to every team menber to check status of their work 7 - Updated the SDD Document and reviwed all other documents | 4 |  |  | 8 |  | 1 |  | 2 |  | 1.Delayed updates from some team members, which made it hard to unblock other developers to work on tasks. 2. Some team members are in different time zones and its getting difficult to setup meetings, also few team menbers have very narrow time slots (1hr)which makes it difficult to find a common time slot for setting up meeting. | 1. Will ask teammates to have standup meeting every other day so that we will be updated with latest issues and blocks. 2. Will ask team member sto have 3-4 hrs of time interval every day so that we can find common time for all team members | Work on iteration 2 tasks | 12

## Zuowen_Tang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 6 | 5 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 2 | 0.5 | 0.5 |  |  | 0.5 | 1 | 0.5 | 1. Create Documents in Team Folder 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. A classmate has dropped out of the class. 2. I Was finishing the final week of BU spring semester. 3. Communication is not clear. We were talking back and forward about the same topic | 1. The spring semester will be ended next week. 2. Try to set up an actual plan and communicate clearly with people | 0 - Set up a clear plan for the summer term | 6
2 | 5/17-5/23

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6