## Sheet1
Test case ID | Test name | New or old | Test items (what do you test ) | Test priority (high/medium/low) | Dependencies (to other test case/requirement if any) | Preconditions (if any) | Input data | Test steps | Postconditions | Expected output | Actual output | Pass Rate | # of Testing | Bug id / Github link | Additional notes
1 | Register an account | New | Registering a new user account | high |  |  | Username Email Password | 1. Visit the registration page. 2. Enter username, email, and password. 3. Go to the email inbox. 4. Click on the confirmation link. 5. Redirect to the login page if the link is valid. |  | When successful, the user will receive a confirmation link through email and jump to the login page upon clicking. | As expected | 90% | 25 | #1 Email authentication can't be sent #2 Configuration of Email Host Password | User Registration, Login, and Profile Management
2 | Logging in | New | Logging in with an existing user account | high |  | Have an activated account | Username Password | 1. Visit the login page. 2. Enter username and password. 3. Redirect to homepage if success. |  | When successful, the user will be able to log in and jump to the homepage page. | As expected | 95% | 15 | #3 Username cannot be entered in caps
3 | Recovering password | New | Recovering lost password | high | login function | Have an activated account | Email | 1. Visit the login page. 2. Click on the 'Forgot Password?' link. 3. Enter the email address of the account 4. Go to the email inbox 5. Click on the reset password email 6. Enter a new password and confirm 7. Go to the login page and login with the new password |  | When successful, the user will receive a password reset link thouthrough email and jump to the password-changing page. Once the password has been changed, the user can log in by using the new password. | As expected | 95% | 15 | #2 Configuration of Email Host Password
4 | Make changes of user profile | New | Editing and saving changes in the user profile | high | login function | Have an activated account |  | 1. Go to the homepage, and click on the 'change password' link. 2. Enter the new password and confirm. 3. Relogin with new password. |  | When successful, the user's password will be changed. | As expected | 95% | 20 | #2 Configuration of Email Host Password
5 | Enter the wrong password when login | New | Purposefully enter the invalid data | medium | login function |  | Username Password | Same as Test#2 but with the wrong password. |  | The webpage shows "invalid email or password" and fail to login. | As expected | 100% | 20
6 | Enter the wrong/invalid email when regist | New | Purposefully enter the invalid data | medium | registration function |  | Username Password Email | Same as Test#1 but with the invalid email, ie. not following the email pattern |  | The webpage shows "invalid input" and fail to register. | As expected | 100% | 20
7 | Adding food items | New | Adding food items | high |  | Login |  | 1. Go to the Food Table page 2. Enter the food name and calorie numbers according to the slots. 3. See the food shown on the table. |  | The webpage shows the input data. | As expected | 100% | 10 |  | Dietary Input and Management
8 | Adding food log | New | Adding food log as a user | high |  | Login |  | 1. Go to the My Food Journal page 2. Choose a food name, serving size according to the slots. 3. See the food shown on the table. |  | The webpage shows the input data. | As expected | 100% | 10
9 | Adding dated log | New | Adding date of the log as a user | high |  | Login |  | 1. Go to the My Food Journal page 2. Choose a food name, serving size, and date according to the slots. 3. See the food shown on the table. |  | The webpage shows the input data. | As expected | 100% | 10
10 | Posting new posts | New | Submit a new post on one's social dashboard | high | login function | Have an activated account and login | Anything text, emojis or links | 1. Go to the social dashboard page. 2. Enter any text content in the post box. 3. Click on the 'Post' button. | User's own dashboard and profile page will show the new post. | The dashboard page auto-refresh and shows the post. | As expected | 100% | 20 |  | Social Media Function
11 | View other's profile and posts | New | View other's profiles and posts | high | login function | Have an activated account and login |  | 1. Go to the other user's profile page by accessing the All Profiles page |  | The webpage shows other user's posts and profile. | As expected | 100% | 20
12 | View all users' profiles | New | View all users' profiles | high | login function | Have an activated account and login |  | 1. Go to the social dashboard page. 2. Click on the 'All Profiles' button. |  | Redirect to the pages that shows all registered users profile. | As expected | 100% | 20
13 | Follow other users | New | Follow other users | high | login function | Have an activated account and login |  | 1. Go to other user's profile. 2. Click on the 'Follow' button. | The followed user's posts will show on your dashboard. | The 'Follow' button turns grey and can't be accessed anymore. | As expected | 100% | 20
14 | Unfollow other users | New | Unfollow other users | high | login function | Have an activated account and login |  | 1. Go to other user's profile. 2. Click on the 'Unfollow' button. | The unfollowed user's posts will be removed from your dashboard. | The 'Unfollow' button turns grey and can't be accessed anymore. | As expected | 100% | 20
15 | Check followers | New | If user is able to see their followers | high | login function | Have an activated account and login |  | 1. Go to the social dashboard page. 2. Check the followers on the right sidebar. |  | The right sidebar will refresh itself whenever someone followed you. | As expected | 100% | 20
16 | Check followed users and their posts | New | If the user is able to check who they followed and view their posts | high | login function | Have an activated account and login |  | 1. Go to the social dashboard page. 2. Check the users you followed on the right sidebar. 3. Check their posts on left side of the page. |  | The right sidebar will refresh itself whenever someone you followed someone. The left main feed screen will show people's, who you followed, posts automaticlly. | As expected | 100% | 20
17
18